# DGOP v6.0 Production Pilot

# Workflow-Prioritized Sprint Definition

| STATUS |  | OWNER |  | LAST UPDATED |
| --- | --- | --- | --- | --- |
| Proposed sprint definition |  | DGOP PMO / Workflow Track Lead |  | August 14, 2026 |

| Field | Value |
| --- | --- |
| Authors | Codex as senior project manager and technical software engineer, using DGOP product architecture guidance |
| Reviewers | DMO lead, Workflow Product Owner, Enterprise Architect, Security Lead, QA Lead, Data Governance SME |
| Related docs | DGOP v6.0 zip analysis; Volume 2 workflow trace; sprint planning assumptions; module interdependency assessment |
| Scope | Two-week Jira-style sprint definition for v6.0 production pilot readiness, with Workflow Canvas / Workflow Engine as a prioritized standalone track |

# 1. Abstract

This document defines a 12-sprint production pilot delivery plan for DGOP v6.0, continuing from the current Sprint 0-43 implementation baseline. The plan prioritizes Workflow Canvas and Workflow Engine as a standalone delivery track while preserving the required interdependencies with asset types, access management, audit, evidence, search, notifications, integrations, security, and operational readiness.

The execution model assumes two-week sprints and a large team working in parallel tracks. Workflow work is front-loaded because Volume 2 Section 23 introduces product-critical behavior: business-node MVP parity, BPMN technical parity, strict Designer/Reviewer/Publisher separation, runtime token traceability, workflow reporting, and all-family regression coverage.

# 2. Goals and Non-Goals

| Goals | Non-goals |
| --- | --- |
| Reach production pilot readiness with explicit readiness gates, sign-off records, and evidence artifacts. | Do not rebuild the platform from scratch; extend the existing Angular/NestJS/Prisma DGOP codebase. |
| Deliver Workflow Canvas business-node MVP parity and phased BPMN technical parity. | Do not make Timer, Sub-Workflow, and Error nodes block the earliest core-flow sprint unless core parity is already stable. |
| Introduce six first-class data asset types and use them as a prerequisite for type-specific access controls. | Do not build access permissions against the current generic asset model as the final target. |
| Make Data Asset Access Management the single asset-level authorization record consumed by ABAC, reviews, enforcement, and reporting. | Do not maintain duplicate authorization truth across RoleDataAccessMap, ABAC, and access matrix records. |
| Keep audit, evidence, RBAC/data scope, search, notification, reporting, and readiness impacts inside every control-object story. | Do not claim all production target integrations are live; OpenSearch, SSO/Nafath, Kafka, Camunda/Zeebe, SIEM, and HSM/KMS may remain target or pilot-specific. |

# 3. Background and Problem Statement

The current DGOP repository already implements a broad governance operations prototype: master data, assets, ownership, workflow, NDI, evidence, scoring, dashboard, training, data quality, security governance, integrations, open data, FOI, privacy, data sharing, search, transparency, reports, audit packs, extended domains, business value, governance operations, and governance lifecycle.

The v6.0 package changes the delivery priority. The platform now needs first-class asset-type governance, a single asset-level access authorization spine, and a Workflow Canvas that is accepted as an executable governance runtime rather than only a route-design surface. Without explicit sprint dependencies, parallel teams could accidentally create duplicate access models, incomplete workflow node behavior, or readiness dashboards that overstate production pilot status.

# 4. Proposed Sprint Architecture

The plan uses six coordinated tracks. Workflow is Track C and receives priority sequencing, but it does not bypass foundational dependencies such as asset types, owner/delegate validation, audit, and readiness gates.

| Track | Responsibility | Primary storage / objects | Failure behavior |
| --- | --- | --- | --- |
| A. Asset Type Foundation | Six asset types, subtype metadata, lifecycle states, Asset 360 type panels, type-aware validation. | DataAsset, reference values, lifecycle status, type-specific metadata. | Access and workflow stories that depend on type-specific behavior cannot exit done. |
| B. Data Asset Access Management | AccessGrant spine, permission catalogues, profiles, matrix, CSV, reviews, enforcement status. | AccessGrant, AccessGrantPermission, profiles, principals, change sets, reviews. | ABAC/enforcement/reporting cannot consume parallel authorization records. |
| C. Workflow Canvas / Engine | Business-node MVP parity, BPMN technical parity, runtime semantics, monitoring, reports, publish governance. | WorkflowTemplate, stages, transitions, versions, runtime tokens, cases, tasks, variables. | Readiness gate blocks production pilot until AC-WF coverage passes or exceptions are signed. |
| D. Security, Identity, Audit | RBAC/data scope, SoD, SSO/Nafath readiness, SIEM mapping, audit chain, evidence controls. | Role/permission/scope, AuditLog, security events, evidence artifacts. | Control stories cannot complete without audit event and authorization tests. |
| E. Search, Notifications, Integrations, Ops | Search registry/indexing, notification delivery, connector contract, readiness gates, production acceptance. | SearchIndexRecord, notifications, connector jobs, readiness/sign-off records. | Operational views must read live state and expose blocked gates. |
| F. QA, Performance, Release | E2E regression, UAT, performance, deployment rehearsal, go/no-go evidence. | Test packs, UAT defects, load results, release package. | No sprint closes with unresolved P0/P1 defects unless formally accepted. |

## Delivery dependency order

Platform guardrails and acceptance gate model.

Six data asset type foundation.

Ownership and delegation validation hardening.

Access grant authorization spine.

Workflow Canvas core parity.

Access matrix UX and access review lifecycle.

Workflow runtime monitoring and reporting parity.

Search, notification, and reporting updates for new objects.

Enforcement connector and production integration pilots.

Production pilot readiness, performance, DR, monitoring, and sign-off.

## Workflow node coverage and sprint priority

This matrix preserves the Volume 2 workflow module details for node types and connectors. Core business flow nodes are scheduled before advanced orchestration and resilience nodes, while each node keeps a clear readiness dependency.

| Node Type | Priority / function | Primary sprint | Readiness dependency |
| --- | --- | --- | --- |
| Start Node | Core mandatory entry point; exactly one active start per workflow. | Sprint 45 | Template validation must block publish when zero or multiple active starts exist. |
| End Node | Core completion and outcome mapping for completed, rejected, cancelled, and failed paths. | Sprint 45 | Outcome mapping must feed monitor, reports, audit timeline, and readiness dashboards. |
| User Task | Core human activity with task name, instructions, assigned user or role, form, due date, reminder, and completion outcome. | Sprints 45-48 | Assignment, form validation, due date, reminder, inbox, and audit events must work before UAT. |
| Approval Task | Core governance decision with approve, reject, return for clarification, comments, approver, and due date. | Sprints 45-48 | SoD, approver assignment, return path, comments, and approval audit evidence must pass. |
| Automated Task | System-executed API invocation, data update, system action, notification action, success, and failure outcomes. | Sprint 50 | Connector model, retry/failure contract, and audit log semantics must be defined before execution. |
| Decision Gateway | Core conditional routing: yes/no, multiple outcomes, default path, AND/OR rules, and DMN-style decision table logic over runtime variables. | Sprints 45-47 | Variable registry, condition evaluator, default path behavior, and negative tests must pass. |
| Parallel Gateway | Core split that starts two or more activities simultaneously. | Sprints 45-47 | Runtime token lineage and monitor path visualization must prove parallel branch creation. |
| Merge Gateway | Core join that combines parallel paths and waits for all incoming branches to complete. | Sprints 45-47 | Token join semantics, stuck-case detection, and regression tests must pass. |
| Timer Node | Advanced pause or redirect by duration, due date, timeout, or SLA expiry. | Sprint 51 | Scheduler, SLA clock, timeout routing, escalation, and evidence capture must be operational. |
| Notification Node | Automation node that sends in-application or email notification. | Sprint 50 | Notification templates, recipient resolution, delivery state, retry, and audit trail must be available. |
| Sub-Workflow Node | Advanced orchestration node that invokes another published workflow. | Sprints 51-52 | Published workflow versioning, child-case linkage, rollback, and migration rules must be ready. |
| Error Node | Advanced resilience node for failed automated activities and workflow exceptions. | Sprint 51 | Failure event taxonomy, retry controls, monitor alerts, and operational metrics must be in place. |

# 5. Request Lifecycle

Every Jira story follows this delivery lifecycle. The lifecycle is intentionally stricter for workflow and access stories because both create governance decisions.

Intake: Product owner or track lead creates a story with actor, business object, lifecycle, control surface, and reporting impact.

Dependency triage: PM, architect, QA, and security mark upstream data model, API/service, permission/audit, readiness, and test dependencies.

Definition of Ready: story has source trace, acceptance criteria, data/API/UI impact, audit events, test IDs, and dependency links.

Sprint commitment: squad accepts only stories whose critical upstream gates are ready or explicitly included in the same sprint.

Implementation: backend, frontend, migration, seed data, permissions, audit, and tests are built as one vertical slice where feasible.

Verification: unit, integration, E2E, accessibility, security, data-scope, and regression tests run against the story's control surface.

Evidence capture: workflow/access stories emit audit evidence and update readiness/reporting signals before the story is accepted.

Sprint demo and close: P0/P1 defects, dependency drift, and readiness gate status are reviewed before sprint closure.

# 6. API and Data Contracts

## Primary Jira story contract

| Field | Type | Required | Description |
| --- | --- | --- | --- |
| Jira ID | String | Yes | Track-prefixed ID such as WF-47-01 or AM-50-02. |
| Epic / Track | Enum | Yes | Asset, Access, Workflow, Security, Operations, QA, Release, Documentation. |
| Primary actor | Enum | Yes | DMO Admin, Data Owner, Steward, Reviewer, Publisher, Auditor, System Actor, Executive. |
| Business object | String | Yes | Asset, access grant, workflow template, task, case, evidence, report, connector, readiness gate. |
| User story | Text | Yes | As a role, I need capability, so governance outcome is achieved. |
| Acceptance criteria | Checklist | Yes | Happy path, negative path, permissions, audit, reporting/readiness, EN/AR where user-facing. |
| Dependencies | Links | Yes | Upstream model/API/control/test dependencies and downstream reporting/readiness consumers. |
| Tests | IDs | Yes | Unit, integration, E2E, regression, performance or UAT test references. |
| Done evidence | Links | Yes | PR/build/test evidence, audit log evidence, screenshots where applicable, readiness status. |

## Definition of Done

Server-side permission and data-scope enforcement exists for all governed writes.

Lifecycle state and validation rules are persisted, not frontend-only.

Audit event includes actor, action, object, previous/new value, decision context, and timestamp.

Search, notification, evidence, reporting, and readiness impacts are updated when the object is operationally visible.

Tests include positive path, negative path, permission denial, and regression coverage.

Production pilot gates are updated or a signed exception is created.

# 7. Consistency, Idempotency, and Replay

| Scenario | Expected behavior | Reasoning |
| --- | --- | --- |
| Duplicate access grant request | Rejected or versioned through one AccessGrant record; no parallel authorization truth is created. | Prevents RoleDataAccessMap, ABAC, and matrix drift. |
| Workflow publish by same designer | Blocked unless a separate reviewer/publisher approves according to permission and SoD rules. | Preserves process-change governance. |
| Repeated workflow task decision | Idempotent handling prevents duplicate downstream actions and token corruption. | Workflow evidence must be replayable. |
| Connector writeback retry | Uses grant/version/action idempotency key and records each attempt. | Prevents duplicate technical provisioning. |
| Readiness gate recalculation | Reads live module data and does not allow manual green status when required P1 gates fail. | Avoids overstated production pilot readiness. |

# 8. Security and Privacy Considerations

Workflow publication requires Designer, Reviewer, and Publisher separation with audit evidence.

Access grant APIs enforce Data Owner or delegated-owner scope server-side.

ABAC simulation consumes the same AccessGrant record used by matrix, reviews, and enforcement.

Exported access CSV files require formula-injection protection, audit, and data-scope filtering.

Pilot security evidence must cover RBAC, data scope, audit chain, SSO/Nafath readiness, SIEM mapping, secret management, backup/DR decisions, and production exception approvals.

No story that writes governance decisions can close without audit events and permission-denial tests.

# 9. Operational Readiness

| Signal | SLO or alert | Owner | Launch gate |
| --- | --- | --- | --- |
| Workflow MVP acceptance | AC-WF-01..17 pass or signed exception | Workflow Track Lead | Required |
| Access Management P1-P3 | Grant/matrix/review/enforcement status accepted | Access Track Lead | Required |
| Performance | Workflow 1,000 concurrent cases; access matrix 500 x 100; CSV 10,000 rows | QA / Performance Lead | Required or exception |
| Search scope safety | Unauthorized results silently excluded; external and DB fallback validated | Search / Security | Required |
| Audit and evidence | All new control objects emit audit and evidence-ready records | Security / Audit Lead | Required |
| Production controls | SSO, SIEM, Vault/KMS/HSM, DR, backups, monitoring documented or exceptioned | DevOps / Security | Required |

# 10. Alternatives Considered

| Alternative | Why it was considered | Why it was not selected |
| --- | --- | --- |
| Workflow last | Asset and access foundations have hard dependencies and could consume early sprints. | User explicitly prioritized workflow; workflow is also a shared case/task layer across DGOP. |
| Single proving workflow | Simplifies acceptance and demo planning. | User requested all workflow families; a single path would hide cross-module regressions. |
| Full BPMN first | Technically pure and closer to target external BPM semantics. | Business-node parity and governed runtime behavior deliver value sooner; full BPMN hardening follows. |
| Access matrix before asset types | Parallel team could start UI sooner. | Type-specific permissions require six asset types first; otherwise rework is likely. |

# 11. Sprint Milestones

| Sprint | Milestone | Deliverable | Exit criteria |
| --- | --- | --- | --- |
| 44 | Program foundation and workflow governance gate | Workflow taxonomy, acceptance registry, SoD publish lifecycle, asset-type model start, production guardrails. | WF-44-01, WF-44-02, WF-44-03, DAT-44-01, SEC-44-01, QA-44-01 |
| 45 | Workflow core palette and asset type foundation | Start/End/User/Approval/Decision/Parallel/Merge nodes, exactly-one start validation, return-for-clarification, asset type fields. | WF-45-01, WF-45-02, WF-45-03, DAT-45-01, DAT-45-02, QA-45-01 |
| 46 | Forms, variables, connectors, and ownership hardening | Workflow variable registry, form builder enforcement, connector type model, owner/delegate validation, type-specific asset validation. | WF-46-01, WF-46-02, WF-46-03, OWN-46-01, DAT-46-01, SEC-46-01 |
| 47 | Runtime tokens and access authorization spine | Token lineage, default path logic, parallel/merge semantics, AccessGrant and permission-profile schema. | WF-47-01, WF-47-02, WF-47-03, AM-47-01, AM-47-02, QA-47-01 |
| 48 | Workflow monitor and access P1 APIs | Execution monitor, richer inbox, operational metrics, grant/modify/revoke APIs, ABAC reads grant model, readiness gates. | WF-48-01, WF-48-02, WF-48-03, AM-48-01, AM-48-02, OPS-48-01 |
| 49 | All-family workflow regression and access matrix UX | Cross-workflow regression, template lifecycle, review-before-publish UI, matrix grid, effective access, search indexing. | WF-49-01, WF-49-02, WF-49-03, AM-49-01, AM-49-02, SEARCH-49-01 |
| 50 | Automation/notification core and access review operations | Automated task runner, notification node execution, success/failure connectors, CSV validate/export/import, review campaigns. | WF-50-01, WF-50-02, WF-50-03, AM-50-01, AM-50-02, QA-50-01 |
| 51 | Advanced workflow nodes and enforcement contract | Timer, sub-workflow, and error node execution after core flows; enforcement connector contract and failure readiness metrics. | WF-51-01, WF-51-02, WF-51-03, INT-51-01, OPS-51-01, QA-51-01 |
| 52 | BPMN technical parity and version migration | Import/export boundary, full validation catalog, version diff/rollback/migration hardening, isolated test instances, enforcement status. | WF-52-01, WF-52-02, WF-52-03, AM-52-01, INT-52-01, SEC-52-01 |
| 53 | Production pilot integration hardening | Workflow and access performance, OpenSearch/fallback, SSO readiness plan, sign-off records, load and E2E test packs. | WF-53-01, AM-53-01, SEARCH-53-01, SEC-53-01, OPS-53-01, QA-53-01 |
| 54 | Pilot UAT and operational readiness | Workflow all-family UAT, Access Management P1-P3 UAT, production acceptance dashboard, control evidence, runbooks. | WF-54-01, AM-54-01, OPS-54-01, SEC-54-01, QA-54-01, DOC-54-01 |
| 55 | Production pilot go/no-go hardening | Workflow and access acceptance closure, performance remediation, go/no-go package, deployment rehearsal, final regression. | WF-55-01, AM-55-01, PERF-55-01, OPS-55-01, REL-55-01, QA-55-01 |

# 12. Detailed Jira Sprint Backlog

Each story below inherits the Jira story contract and Definition of Done in Section 6. Workflow stories are intentionally prioritized inside each sprint, and advanced workflow nodes are scheduled after core user, approval, decision, and parallel flows stabilize.

## Sprint 44 - Program foundation and workflow governance gate

Sprint goal: Workflow taxonomy, acceptance registry, SoD publish lifecycle, asset-type model start, production guardrails.

| Jira ID | P | Track | Story | Depends on | Acceptance / test focus |
| --- | --- | --- | --- | --- | --- |
| WF-44-01 | P0 | Workflow | Normalize workflow node taxonomy and AC-WF trace registry | None | Node names map to Volume 2 23.3; AC-WF-01..17 baseline exists; tests fail on unmapped nodes. |
| WF-44-02 | P0 | Workflow | Design Designer/Reviewer/Publisher lifecycle model | WF-44-01 | Draft -> Under Review -> Published/Active lifecycle is modeled; SoD rules and audit events specified. |
| WF-44-03 | P0 | Workflow | Create workflow MVP acceptance gate in readiness model | WF-44-01 | Readiness reports blocked until core Workflow Canvas gates pass. |
| DAT-44-01 | P0 | Asset | Create six asset type reference model and migration plan | None | Dataset, File, Document/Record, API/Data Feed, BI Report/Dashboard, AI Product are configurable and seeded. |
| SEC-44-01 | P0 | Security | Define production pilot guardrail baseline | None | RBAC, data scope, audit, secret, SIEM, SSO, DR, performance guardrails have owners and evidence needs. |
| QA-44-01 | P0 | QA | Create cross-track dependency and test matrix | All analysis artifacts | Every story has dependency, test, audit, and readiness fields. |

## Sprint 45 - Workflow core palette and asset type foundation

Sprint goal: Start/End/User/Approval/Decision/Parallel/Merge nodes, exactly-one start validation, return-for-clarification, asset type fields.

| Jira ID | P | Track | Story | Depends on | Acceptance / test focus |
| --- | --- | --- | --- | --- | --- |
| WF-45-01 | P0 | Workflow | Implement core Workflow Canvas palette entries | WF-44-01 | Start, End, User Task, Approval Task, Decision Gateway, Parallel Gateway, Merge Gateway appear in palette and persist. |
| WF-45-02 | P0 | Workflow | Enforce start/end validation and outcome mapping | WF-45-01 | Exactly one active Start is required; End outcomes include completed, rejected, cancelled, failed. |
| WF-45-03 | P0 | Workflow | Add return-for-clarification approval decision | WF-45-01 | Approval tasks support approve, reject, return; comments and audit are mandatory. |
| DAT-45-01 | P0 | Asset | Add assetType, subtype, and v6 lifecycle states to DataAsset | DAT-44-01 | APIs and Prisma model persist type/subtype and registered/under review/active/suspended/retired/archived states. |
| DAT-45-02 | P1 | Asset | Add Asset 360 type-aware panel skeletons | DAT-45-01 | Each of six asset types renders a type-aware panel and empty state. |
| QA-45-01 | P0 | QA | Run existing workflow family regression baseline | WF-45-01 | Current ownership, DQ, FOI, privacy, open data, data sharing flows still pass. |

## Sprint 46 - Forms, variables, connectors, and ownership hardening

Sprint goal: Workflow variable registry, form builder enforcement, connector type model, owner/delegate validation, type-specific asset validation.

| Jira ID | P | Track | Story | Depends on | Acceptance / test focus |
| --- | --- | --- | --- | --- | --- |
| WF-46-01 | P0 | Workflow | Create workflow variable registry and typed variable model | WF-45-01 | Text, number, boolean, date, user, role, list variables are defined and available to conditions. |
| WF-46-02 | P0 | Workflow | Harden task form builder and runtime validation | WF-46-01 | User/approval forms support required fields, typed validation, attachments, and audit on submit. |
| WF-46-03 | P0 | Workflow | Make connector types explicit | WF-45-01 | Sequence, conditional, default, success, failure, timeout, return connectors persist as typed properties. |
| OWN-46-01 | P0 | Ownership | Harden owner/delegate validation service | DAT-45-01 | Access and workflow write paths can verify active owner or approved delegate server-side. |
| DAT-46-01 | P1 | Asset | Implement type-specific asset validation and imports | DAT-45-01 | Unsupported fields and invalid lifecycle transitions are rejected; import preview identifies type errors. |
| SEC-46-01 | P0 | Security | Publish workflow and asset audit event catalog | WF-46-02, DAT-46-01 | Audit event names, metadata, actor, object, previous/new values are documented and emitted in core paths. |

## Sprint 47 - Runtime tokens and access authorization spine

Sprint goal: Token lineage, default path logic, parallel/merge semantics, AccessGrant and permission-profile schema.

| Jira ID | P | Track | Story | Depends on | Acceptance / test focus |
| --- | --- | --- | --- | --- | --- |
| WF-47-01 | P0 | Workflow | Extend runtime token lineage and token API | WF-46-03 | Runtime tokens include parent/branch context and can be queried for visual trace. |
| WF-47-02 | P0 | Workflow | Implement decision default path and condition evaluation | WF-46-01, WF-46-03 | Decision gateways reject missing default paths and evaluate variable conditions deterministically. |
| WF-47-03 | P0 | Workflow | Generalize parallel/merge runtime semantics | WF-47-01 | Parallel branches fork tokens and merge only after all incoming branches complete. |
| AM-47-01 | P0 | Access | Create AccessGrant core schema and lifecycle | DAT-45-01, OWN-46-01 | Grant links asset, principal, dates, justification, version, status, owner decision, enforcement status. |
| AM-47-02 | P0 | Access | Create permission catalogue and profile schema | DAT-45-01 | Permissions and profiles are versioned by asset type; unsupported permissions are blocked. |
| QA-47-01 | P0 | QA | Create token trace and decision gateway tests | WF-47-01, WF-47-02 | Automated tests cover start, decision, branch, parallel, merge, and final paths. |

## Sprint 48 - Workflow monitor and access P1 APIs

Sprint goal: Execution monitor, richer inbox, operational metrics, grant/modify/revoke APIs, ABAC reads grant model, readiness gates.

| Jira ID | P | Track | Story | Depends on | Acceptance / test focus |
| --- | --- | --- | --- | --- | --- |
| WF-48-01 | P0 | Workflow | Build execution monitor with path highlights | WF-47-01, WF-47-03 | Monitor shows completed, active, pending, failed nodes and route path. |
| WF-48-02 | P0 | Workflow | Enrich work inbox and task action UX | WF-46-02, WF-45-03 | Inbox supports form completion, approve/reject/return, comments, attachments, and history. |
| WF-48-03 | P0 | Workflow | Add workflow operational reporting metrics | WF-48-01 | Initiated, active, completed, failed, average completion, overdue, SLA metrics are available. |
| AM-48-01 | P0 | Access | Implement grant, modify, revoke APIs | AM-47-01, AM-47-02, OWN-46-01 | Data Owner can grant/modify/revoke only owned assets; every change is versioned and audited. |
| AM-48-02 | P0 | Access | Rewire ABAC simulation to consume AccessGrant | AM-48-01 | ABAC no longer uses a parallel authorization truth; decisions cite the grant version used. |
| OPS-48-01 | P0 | Ops | Add Workflow MVP and Access P1 readiness gates | WF-48-03, AM-48-01 | Production acceptance cannot pass while gates are unmet. |

## Sprint 49 - All-family workflow regression and access matrix UX

Sprint goal: Cross-workflow regression, template lifecycle, review-before-publish UI, matrix grid, effective access, search indexing.

| Jira ID | P | Track | Story | Depends on | Acceptance / test focus |
| --- | --- | --- | --- | --- | --- |
| WF-49-01 | P0 | Workflow | Create all-family workflow regression pack | WF-48-02 | Ownership, DQ, FOI, open data, privacy, data sharing, NDI, access review flows have regression tests. |
| WF-49-02 | P0 | Workflow | Complete workflow template lifecycle states | WF-44-02 | Draft, Under Review, Published, Active, Suspended, Retired, Archived are enforced. |
| WF-49-03 | P0 | Workflow | Implement review-before-publish UI and API | WF-44-02, WF-49-02 | Designer cannot publish own draft; reviewer comments and publisher action are audited. |
| AM-49-01 | P0 | Access | Build access matrix grid and cell editor | AM-48-01 | Owners see owned assets, role/group columns, current profiles, statuses, and type-specific permissions. |
| AM-49-02 | P1 | Access | Implement effective access display | AM-48-01 | Effective access expands grant, role/group, status, date range, and enforcement caveat. |
| SEARCH-49-01 | P1 | Search | Index new v6 objects | DAT-45-01, AM-48-01, WF-49-02 | Asset types, grants, workflow definitions, and readiness gates are searchable with scope filters. |

## Sprint 50 - Automation/notification core and access review operations

Sprint goal: Automated task runner, notification node execution, success/failure connectors, CSV validate/export/import, review campaigns.

| Jira ID | P | Track | Story | Depends on | Acceptance / test focus |
| --- | --- | --- | --- | --- | --- |
| WF-50-01 | P0 | Workflow | Implement automated task runner MVP | WF-46-03, WF-47-01 | Configured service/system actions execute with timeout, retry, success/failure state, and audit. |
| WF-50-02 | P0 | Workflow | Implement notification node execution MVP | WF-50-01 | In-app and email notification actions execute from workflow nodes and record delivery attempts. |
| WF-50-03 | P0 | Workflow | Execute success/failure connector semantics | WF-46-03, WF-50-01 | Automated tasks route to success/failure branches deterministically. |
| AM-50-01 | P0 | Access | Implement CSV export/import validate-only flow | AM-49-01 | Template, export, validate-only import, row errors, and grant version checks are available. |
| AM-50-02 | P1 | Access | Implement periodic access review campaign | AM-49-02 | Reviewer certifies, modifies, or revokes grants; evidence snapshots are produced. |
| QA-50-01 | P0 | QA | Run access/workflow integrated E2E suite | WF-50-03, AM-50-02 | Workflow-driven access review and grant changes pass end-to-end with audit. |

## Sprint 51 - Advanced workflow nodes and enforcement contract

Sprint goal: Timer, sub-workflow, and error node execution after core flows; enforcement connector contract and failure readiness metrics.

| Jira ID | P | Track | Story | Depends on | Acceptance / test focus |
| --- | --- | --- | --- | --- | --- |
| WF-51-01 | P1 | Workflow | Implement timer node scheduling and timeout routing | WF-50-03 | Timer nodes wait or redirect by duration, due date, SLA expiry, and timeout connector. |
| WF-51-02 | P1 | Workflow | Implement sub-workflow invocation | WF-47-01, WF-46-01 | Published child workflows can be invoked with variable mapping and parent/child trace. |
| WF-51-03 | P1 | Workflow | Implement error node handling and retry controls | WF-50-03 | Failed automated nodes route to Error node; monitors expose retry/cancel controls. |
| INT-51-01 | P1 | Integration | Define access enforcement connector contract | AM-48-01 | Grant/update/revoke/verify/test/retry operations and idempotency keys are specified. |
| OPS-51-01 | P1 | Ops | Add workflow failure readiness metrics | WF-51-03 | Failed automation, timer breach, retry counts, and unresolved incidents appear in readiness. |
| QA-51-01 | P1 | QA | Create advanced node test pack | WF-51-01, WF-51-02, WF-51-03 | Timer, sub-workflow, and error node happy/negative paths are covered. |

## Sprint 52 - BPMN technical parity and version migration

Sprint goal: Import/export boundary, full validation catalog, version diff/rollback/migration hardening, isolated test instances, enforcement status.

| Jira ID | P | Track | Story | Depends on | Acceptance / test focus |
| --- | --- | --- | --- | --- | --- |
| WF-52-01 | P1 | Workflow | Harden BPMN import/export and validation boundary | WF-51-03 | Supported vs unsupported BPMN constructs are explicit; invalid imports fail with clear errors. |
| WF-52-02 | P0 | Workflow | Harden version diff, rollback, and active-case migration | WF-49-02 | Migration previews affected cases; rollback preserves audit and active instance behavior. |
| WF-52-03 | P0 | Workflow | Create isolated workflow test-instance space | WF-48-01 | Test runs never create production cases; test variables and path are inspectable and resettable. |
| AM-52-01 | P1 | Access | Implement enforcement status and manual provisioning task | AM-50-01, INT-51-01 | Pending, partial, failed, enforced states are shown; manual evidence confirms completion. |
| INT-52-01 | P1 | Integration | Pilot one priority enforcement connector mode | INT-51-01, AM-52-01 | Manual, hybrid, or registry-only connector records attempts and results. |
| SEC-52-01 | P1 | Security | Map workflow/access events to SIEM evidence model | WF-52-02, AM-52-01 | Security event mapping is documented and test events can be exported. |

## Sprint 53 - Production pilot integration hardening

Sprint goal: Workflow and access performance, OpenSearch/fallback, SSO readiness plan, sign-off records, load and E2E test packs.

| Jira ID | P | Track | Story | Depends on | Acceptance / test focus |
| --- | --- | --- | --- | --- | --- |
| WF-53-01 | P0 | Workflow | Run workflow performance and concurrency validation | WF-52-03 | 1,000 concurrent workflow cases target is tested or exception-recorded with mitigation. |
| AM-53-01 | P0 | Access | Run access matrix and CSV performance validation | AM-52-01 | 500 x 100 matrix and 10,000-row CSV targets are tested or exception-recorded. |
| SEARCH-53-01 | P1 | Search | Validate OpenSearch target and DB fallback | SEARCH-49-01 | External search config and fallback behavior are proven without leaking unauthorized results. |
| SEC-53-01 | P1 | Security | Prepare SSO/Nafath production pilot interface plan | SEC-44-01 | OIDC/SAML claims, roles, scopes, and fallback login policy are documented. |
| OPS-53-01 | P0 | Ops | Implement sign-off record model for pilot gates | OPS-48-01 | Approver, date, decision, exception, and evidence links are persisted. |
| QA-53-01 | P0 | QA | Assemble load, security, and E2E pilot test pack | WF-53-01, AM-53-01 | Pilot test pack can be rerun before go/no-go. |

## Sprint 54 - Pilot UAT and operational readiness

Sprint goal: Workflow all-family UAT, Access Management P1-P3 UAT, production acceptance dashboard, control evidence, runbooks.

| Jira ID | P | Track | Story | Depends on | Acceptance / test focus |
| --- | --- | --- | --- | --- | --- |
| WF-54-01 | P0 | Workflow | Run all-family Workflow Canvas UAT | WF-53-01 | Every workflow family validates core path, decision path, approval path, audit, and reporting. |
| AM-54-01 | P0 | Access | Run Access Management P1-P3 UAT | AM-53-01 | Matrix, grants, CSV, reviews, enforcement status, and audit pass UAT. |
| OPS-54-01 | P0 | Ops | Complete production acceptance dashboard | OPS-53-01 | Dashboard reads live gate state and blocks completion on failed Workflow/Access gates. |
| SEC-54-01 | P0 | Security | Produce pilot controls evidence pack | SEC-52-01, SEC-53-01 | RBAC, data scope, audit, SSO plan, secrets, SIEM, DR exceptions are evidenced. |
| QA-54-01 | P0 | QA | Triage and remediate UAT defects | WF-54-01, AM-54-01 | All P0/P1 defects are closed or accepted by governance sign-off. |
| DOC-54-01 | P1 | Docs | Create admin, operator, and support runbooks | OPS-54-01 | Runbooks cover workflow, access, readiness, support, rollback, and incident handling. |

## Sprint 55 - Production pilot go/no-go hardening

Sprint goal: Workflow and access acceptance closure, performance remediation, go/no-go package, deployment rehearsal, final regression.

| Jira ID | P | Track | Story | Depends on | Acceptance / test focus |
| --- | --- | --- | --- | --- | --- |
| WF-55-01 | P0 | Workflow | Close Workflow Canvas acceptance criteria | WF-54-01 | AC-WF-01..17 pass or have signed exception with mitigation. |
| AM-55-01 | P0 | Access | Close Access Management acceptance criteria | AM-54-01 | AC-AM P1-P3 pass or have signed exception with mitigation. |
| PERF-55-01 | P0 | Performance | Close performance exceptions and remediation plan | WF-53-01, AM-53-01 | Performance evidence, exceptions, and mitigations are signed. |
| OPS-55-01 | P0 | Ops | Produce production pilot go/no-go package | OPS-54-01, PERF-55-01 | Gate decisions, evidence, risks, rollback, support, and owners are complete. |
| REL-55-01 | P0 | Release | Run deployment rehearsal and rollback drill | OPS-55-01 | Pilot deployment and rollback steps are rehearsed with timestamps and owners. |
| QA-55-01 | P0 | QA | Run final regression and release candidate check | All P0 stories | API, web, Prisma, security, accessibility, E2E, and smoke checks pass. |

# 13. Decision and Next Steps

Proceed with a 12-sprint production pilot readiness plan using two-week sprints and parallel tracks. Workflow Canvas / Workflow Engine remains its own prioritized track. Sprint execution must preserve the dependency model: asset types before type-specific access, owner/delegate validation before grants, grants before ABAC/enforcement/reviews, and core workflow runtime semantics before advanced nodes.

Immediate next step: convert this sprint definition into the team's Jira backlog, using WF/AM/DAT/SEC/OPS/QA/REL prefixes and preserving dependency links, acceptance criteria, test IDs, audit requirements, and readiness gates.

Use footnotes for definitions, assumptions, or terms that need precision without interrupting the main narrative.